## Sheet1
Research Schedule 2014 - 23 weeks
Start - Jan 2, 2014
Estimated Paper Deadline - June 12, 2014
PGAS Conference Eugene, Oregon - October 7-10, 2014
Miletstones
Finish Cyclic Implementation
Finish Block Cyclic implementation
Test Implementation on 15 benchmarks
Crafting the Paper
Extra Compiler Tasks - Not Imperative to Completing Paper
Submission to PGAS Conference
Tasks |  |  | Time to Complete (weeks) | Date Completed | Person Responsible for Task
Finish Cyclic Implementation
1 | Implement bounding memory usage (with strip mining) |  | 1 | 2014-01-09 | Aroon
Finish Block Cyclic implementation
2 | Implement bounding memory usage (with strip mining) |  | 1 | 2014-01-16 | Aroon
Test Implementation on 15 benchmarks
3 | Collect 15 appropriate and diverse parallel benchmarks (from Chapel directory or Polybench) |  | 1 | 2014-01-09 | Josh
4 | For each benchmark implement parallel computation with zippered iteration |  | 2 | 2014-01-23 | Josh
5 | For each benchmark add functionality to confirm correctness of calculation, calculate runtime, message count, and message volume (for modulo unrolling cases only) |  | 2 | 2014-02-06 | Josh
6 | For each benchmark collect correctness, runtime, message count, and message volume (for modulo unrolling cases only) for all 30 configurations over 5 input sizes (see excel spreadsheet). |  | 2 | 2014-02-20 | Josh/Aroon
This should be done on the actual cluster computers at LTS but should be checked to work first on a local computer simulating multiple locales.
This step involves filling in the benchmark results tables.
7 | Order configurations from least advanced to most advanced |  | 1 | 2014-01-23 | Aroon
Crafting the Paper
8 | Find relevant sources, relevant literature, past studies done |  | 2 | 2014-02-06 | Aroon
9 | Analyze data - comparing runtime, message count, and message volume to the best existing implementations |  | 2 | 2014-03-06 | Aroon
10 | Build tools to evaluate best existing implementations if they aren’t evaluated yet |  | 2 | 2014-03-20 | Aroon
11 | Develop structure of paper - tentative sections: Introduction, Related Work, Methods (possibly multiple sections for this), Results, Conclusions |  | 1 | 2014-03-27 | Aroon
12 | First Draft of Paper |  | 2 | 2014-04-10 | Aroon
13 | Receive Feedback and refine draft |  | 2 | 2014-04-24 | Aroon
Extra Compiler Tasks - Not Imperative to Completing Paper
14 | Integrate conversion of affine array accesses in loops to zippered iteration |  | 2 | 2014-03-06 | Josh/Aroon
Submission to PGAS Conference |  |  | 1 | 2014-05-01 | Aroon
|  | Total | 24